Notes of the Brinkburn & Hesleyhurst Parish Climate Change & Biodiversity Steering Committee

Meeting on: 		Tuesday 8th April 2025

Meeting at:		Longframlington Memorial Hall

Meeting Time:		7.30 p.m.

Present:			Brenda Barker (BB), Des Barker (DB), Mark Fenwick (MF), Roger Powell, Jackie Scarpa (JS), Cllr 				Jamie Whicker (JW) – Chair.

In attendance:		Clerk: Garth Rhodes.

The meeting opened at 7.31 p.m.

- Apologies. Judith Baker (JB)

- Notes of Previous Meeting held on Wednesday 19th February 2024. The notes were agreed and unanimously approved as a true record.

- Matters arising not appearing elsewhere in the agenda. None

- Membership of the Committee. Jane Elphick had shown interest. JW to follow up. 				Action: JW

- Financial Report.

  - WWCF 107. Approved.

| Expenditure Incurred | Invoice Detail | Invoice Value Total (Net) £ |  | VAT £ | Total (Gross) £ |
| --- | --- | --- | --- | --- | --- |
| Capital Items i.e. equipment (please list as per application form) |  |  |  |  |  |
| Trees for hedging | Invoice 008 | 257.50 |  | 33.50 | 291.00 |
| Revenue Items (please list as per application form) |  |  |  |  |  |
| MKM toilet hire | Invoice 001 | 96.00 |  | 19.20 | 115.20 |
| Hedge laying & Training | Invoice 002 | 2187.70 |  | 436.14 | 2616.84 |
| Tie back x 3 trees | Invoice 003 | 30.00 |  | 0.00 | 30.00 |
| Weeding around paving | Invoice 004 | 80.00 |  | 0.00 | 80.00 |
| Fencing Works | Invoice 005 | 456.00 |  | 91.20 | 547.20 |
| Paint fence/gate/benches | Invoice 006 | 292.00 |  | 0.00 | 292.00 |
| Tidy playing field entrance | Invoice 007 | 80.00 |  | 0.00 | 80.00 |
| Scything wild flowers | Invoice 009 | 40.00 |  | 0.00 | 40.00 |
| Planting trees | Invoice 010 | 116.00 |  | 0.00 | 116.00 |
| Cutting Hedge | Invoice 011 | 160.00 |  | 0.00 | 160.00 |
| Clearing buffer zone | Invoice 012 | 150.00 |  | 0.00 | 150.00 |
| Total Expenditure £ |  | 3938.20 |  | 580.04 | 4518.24 |
| Less grant previously paid |  |  | £ 3034 |  |  |
| ### Total final payment to claim |  |  | £ 904 |  |  |

  - WWCF 116. Approved.

| Date | Projects | Budget | Expend (inc VAT) | Expend (Ex VAT) | Agreed Expend | Balance |
| --- | --- | --- | --- | --- | --- | --- |
|  | A. Hedge laying. |  |  |  |  |  |
| 19/03/2025 | Training, ins/ance, 1st aid, tool hire D Boyson |  | 420.00 | 350.00 |  | -350.00 |
| 11/12/2024 | Training, ins/ance, 1st aid, tool hire D Boyson | 2620.00 | 1260.00 | 1050.00 |  | 1570.00 |
| 25/03/2025 | Toilet hire and cleaning Nixon Hire |  | 126.00 | 105.00 |  | -150.00 |
| 25/01/2024 | Toilet hire and cleaning Nixon Hire | 180.00 | 126.00 | 105.00 |  | 75.00 |
|  | Brash removal disposal Henzell Enterprise | 200.00 |  |  |  | 200.00 |
|  | Refreshments for competitors Sainsburys | 80.00 |  |  |  | 80.00 |
|  | Tree guard disposal | 45.00 |  |  |  | 45.00 |
|  | Additional plants Stanton nursery | 125.00 |  |  |  | 125.00 |
| 15/12/2024 | Preparation & Planting of Buffer zone |  |  | 315.00 |  | -315.00 |
|  | Removal of Wildflower cuttings during 2025 |  |  |  | 50.00 | -50.00 |
|  | Cutting laid hedge during 2025 |  |  |  | 180.00 | -180.00 |
|  | Maintenance of Buffer zone during 2025 |  |  |  | 160.00 | -160.00 |
|  |  | 3250.00 |  | 1575.00 | 390.00 | 1285.00 |
|  | B. Baseline survey and data recording. |  |  |  |  |  |
|  | Echo meter x2 (bat detector) | 154.17 |  |  |  | 154.17 |
| 29/01/2025 | Loupe magnification lens | 23.33 |  | 14.99 |  | 8.34 |
| 29/01/2025 | Weather writer A4 field pouch | 29.16 |  | 14.99 |  | 14.17 |
| 29/01/2025 | x2 Rucksacks for carrying equipment | 34.99 |  | 31.90 |  | 3.09 |
| 29/01/2025 | Pukka note pads x3 | 12.99 |  | 10.76 |  | 2.23 |
| 29/01/2025 | Pencil sharpeners x2 |  |  | 3.36 |  | -3.36 |
| 29/01/2025 | HB pencils x18 | 2.50 |  | 4.83 |  | -2.33 |
|  | Microsoft business standard | 123.60 |  |  |  | 123.60 |
|  | Qgis mapping surveying course 2 people | 200.00 |  |  |  | 200.00 |
|  |  | 580.74 |  | 80.83 | 0.00 | 499.91 |
|  | C. Meadow seeding, scything, and baling. |  |  |  |  |  |
| 04/09/2024 | Traditional baler Ryehill community | 200.00 |  | 200.00 |  | 0.00 |
| 01/09/2024 | Scythes x 6 ,3 training days, sharp/stones x6 | 1348.00 |  | 1348.00 |  | 0.00 |
| 09/12/2024 | Seeds for meadow making Kevin Wharf | 80.00 |  | 80.00 |  | 0.00 |
|  |  | 1628.00 |  | 1628.00 | 0.00 | 0.00 |
|  | D. Bird nest box scheme. |  |  |  |  |  |
| 01/09/2024 | 50 x nest box’s Roger Powell 2024 | 929.42 | 946.92 | 930.09 |  | -0.67 |
| 01/09/2024 | 45 x nest boxes . Barn community workshop. 2024 | 450.00 |  | 450.00 |  | 0.00 |
| 23/02/2025 | 60 x nest box’s Roger Powell 2025 |  | 973.25 | 961.98 |  | -961.98 |
| 2025 | 60x nest boxes . Barn community workshop. |  |  |  | 600.00 | -600.00 |
|  |  | 1379.42 |  | 2342.07 | 600.00 | -1562.65 |
|  | E. River quality testing. |  |  |  |  |  |
|  | Replacement Testing Kit |  |  |  |  |  |
| 09/02/2025 | 1x reel rope |  | 4.73 | 3.94 |  | -3.94 |
| 09/02/2025 | 1x collapsable bucket (unable to get VAT receipt) |  | 6.95 | 6.95 |  | -6.95 |
| 09/02/2025 | Telescopic Water sampler |  | 64.80 | 54.00 |  | -54.00 |
| 09/02/2025 | Ammonia Tests |  | 32.98 | 27.48 |  | -27.48 |
| 09/02/2025 | Phosphate Checker and Reagent NO VAT |  | 106.19 | 106.19 |  | -106.19 |
| 09/02/2025 | x1 PH Water Tester, x1 TDS Meter |  | 55.98 | 46.66 |  | -46.66 |
| 10/02/2025 | E.coli test kits costs with lab tests x 5 | 935.00 | 499.98 | 416.65 |  | 518.35 |
|  |  | 935.00 |  | 661.87 | 0.00 | 273.13 |
|  | F. Litter reduction awareness project. |  |  |  |  |  |
|  | 6x litter signs, 2x litter signs. | 135.77 |  |  |  | 135.77 |
| 29/01/2025 | First Aid Kits x 2 |  |  | 24.14 |  | -24.14 |
| 29/01/2025 | 50x nitrile gloves. |  |  | 4.99 |  | -4.99 |
|  |  | 135.77 |  | 29.13 | 0.00 | 106.64 |
|  | G. Biodiversity event. |  |  |  |  |  |
| 01/09/2024 | Food x 50 people Wingate's village hall | 250.00 |  | 250.00 |  | 0.00 |
|  | Crafts etc. | 79.89 |  |  |  | 79.89 |
| 03/07/2024 | x100 White paper cups |  | 7.95 | 6.62 |  | -6.62 |
| 03/07/2024 | x100 Insulated paper cups |  | 9.20 | 7.67 |  | -7.67 |
| 03/07/2024 | x 360 disposable wooden cutlery |  | 15.58 | 12.98 |  | -12.98 |
| 03/07/2024 | x100 Napkins |  | 4.99 | 4.16 |  | -4.16 |
| 03/07/2024 | x125 plates |  | 16.99 | 14.16 |  | -14.16 |
| 03/07/2024 | Wooden Teaspoons no VAT |  | 4.99 | 4.99 |  | -4.99 |
| 03/07/2024 | Wild Bird Seed no VAT |  | 20.49 | 20.49 |  | -20.49 |
| 03/07/2024 | Craft paper |  | 5.99 | 4.99 |  | -4.99 |
| 06/07/2025 | Beverages | 35.72 |  | 32.95 |  | 2.77 |
| Jul-25 | Biodiversity Event 2025 |  |  |  | 450.00 | -450 |
|  |  | 365.61 |  | 359.01 | 450.00 | -443.40 |
|  | H. ADMINSTRATION COSTS |  |  |  |  |  |
|  | Quarterly Admin costs | 1200.00 |  | 804.00 |  | 396.00 |
|  | Accounts and reports |  |  |  | 400.00 | -400.00 |
|  | Contingency | 525.46 |  |  |  | 525.46 |
|  |  | 1725.46 |  | 804.00 | 400.00 | 521.46 |
|  | TOTAL | 10000.00 |  | 7479.91 | 1840.00 | 680.09 |
|  | Total Grant received to date | 7500.00 |  |  |  |  |
|  | Total Expenditure to date | 7479.91 |  |  |  |  |
|  | Balance Remaining | 20.09 |  |  |  |  |
|  | Expected Expenditure | 1840.00 |  |  |  |  |
|  | Predicted Underspend | 680.09 |  |  |  |  |

- Wingates Windfarm Community Fund.

  - To discuss any current issues including WWCF 107 final report: The final report had been submitted to and signed off by WWCF. They had concluded that there was an error in the report, as only £904 balance on the grant had been requested, (as this was the balance of the full amount of expenditure ex VAT as per WWCF regulation for organisations who were able to reclaim VAT), rather than the full balance of the grant of £1019 . The amended amount of the full outstanding balance of  £1019 was paid into the BHPC account on 31.03.25

  - To discuss future funding applications. It was agreed to ask Julia Plinston for the current WWCF 116 to be extended through 2025/26 to cover expected costs and to inform her that once there was clarity on the future of the Rothbury Estate with an agreed biodiversity plan. that a further bid to WWCF could be expected.				                         Action: JW

- Strand & Project Reports.

  - Hedgelaying. The current activity had now come to an end. Further work to be planned for the autumn. It was agreed not to trim/cut back the buffer zone and laid hedges at the playground this year, to allow new growth to take hold. 	       Action: JW

  - Bird boxes. During February and March 2025, 60 new nest boxes had been constructed and painted with wood preservative and consisted of 15 each for Nuthatch, Redstart, Pied Flycatcher and Spotted Flycatcher. These were to be erected on trees in the parish from late July onwards, when the breeding season will be over. The Rothbury Workshop to provide a further 60 boxes (for the same species, in the same amounts) during summer 2025 for erection in the Autumn.  By late Autumn 2025 a further 120 new boxes will then have been in the parish: a grand total to date of 283 boxes.  Once permission given for the Rothbury Estate, work would begin to start fixing boxes to trees along the Maglin Burn, Forestburn and Todburn.

  - Litter Picking. In all there had been four litter picking events covering  Weldon Bridge to Cragend and Newhouses to Longframlington with c50 bags of rubbish collected.

  - Biodiversity Event. This to take place: Saturday 28th June 2025 (to be funded from WWCF 116).		Action: JS/ALL

  - Wildflower Areas. The focus during the forthcoming season will be on scything the areas.

  - River Testing. Testing along the whole of the Coquet (including the BHPC section) was continuing at a steady pace and building a significant amount of important data. Testing had begun between Longhorsley and West Thirston. CRAG was applying for Blue Water Bathing status at Amble and the E-coli testing programme and results along the river would provide important data for this. JS raised concerns about the sewage treatment plant for Embleton Terrace and the severity of discharge. She agreed to ascertain the status of the plant. If the plant was found not to be working effectively then a reed bed scheme may be the way to mitigate the problem.								         	         Action: JS

  - Habitat Survey. JB had undertaken a substantial amount of work to update the data and produce guidance for users. She had now sent back the Toughbook by courier, and this was expected within the next few days (agreed to pay courier fees from project funds). BB and DB would now be able to continue survey work. Additional volunteer support was needed. BB/DB to monitor the battery situation for the Toughbook and whether some form of sun screen shield was required. Clerk to print off QGIS record sheets as required.							 		Action: BB/DB

- To discuss sale of the Rothbury Estate and next steps. The Lee Farm had been put out to tender for a 3-year contract. This indicated that the present landowners were carrying on with ‘business as usual’ whilst negotiations for the sale of the estate continued.  Committee members were concerned about the nature and extent of the proposed tree planting at Wards Hill  It was agreed to invite Duncan Hutt, Director of Conservation, Northumberland Wildlife Trust to our 10th June  meeting so that he could provide an overview of the status of the sale and future direction of the estate and allow the committee the opportunity to question him about this matter. The position of Community Liaison Officer for the Estate was currently being recruited. Once filled it was hoped more direct and positive  communication between the Wildlife Trusts and the BHPC would ensue.			       Action: JW

- To consider for approval the Biodiversity & Climate Change Protocol & Landowner Agreement Document. The members agreed the final draft (with some further minor amendments). Once completed, online copies to be held with Project Leads, to be issued as required.												   Action: Clerk

- Volunteering: Volunteer Information pack.  This work was still outstanding. JW/Clerk to meet to move forward on this.										             			              Action: JW/Clerk

- To discuss matters in relation to Communications & Media. JW had produced two articles to be placed in the local media (Over the Bridges, Longhorsley Tree, FramNews, NGH Digest, Parish Webpage), one a general report and the other specifically about the hedgelaying project.				             					             Action: JW /Clerk

- Any Other Business. None

- Date of Next Meeting Tuesday 10 June 2025, Longframlington Memorial Hall at 7.30 p.m.

Garth Rhodes, Clerk, 5 Wardle Terrace, Longframlington, NE65 8AB,

Tel: 01665 570347

Email: Clerk@Brinkburn.net

Meeting closed at 9.04 p.m.

Garth Rhodes, Clerk, 5 Wardle Terrace, Longframlington, NE65 8AB,

Tel: 01665 570347 Email: Clerk@Brinkburn.net